## HIV CD&R Communications
| Community Engagement and Response | Q1 | [14 empty] | Q2 | [14 empty] | Q3 | [14 empty] | Q4
|  | JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
|  | 4 | 11 | 18 | 25 | - | 1 | 8 | 15 | 22 | 29 | 7 | 14 | 21 | 28 | - | 4 | 11 | 18 | 25 | - | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | - | 4 | 11 | 18 | 25 | - | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | - | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | - | 5 | 12 | 19 | 26 | -
Planning
IN PROGRESS | Plan progress | [25 empty] | Route to Jean Gibson for Copy Edits |  | Internal routing |  |  |  | Plan due to CDC July 15
internal/NASTAD | NASTAD CD&R community input meetings |  |  |  | TA request to CDC |  | FEBRUARY 8: TA planning meeting 2/11,; FEBRUARY 22: begin planning for NASTAD; MARCH 14: determined survey use, sent survey for approval; MARCH 28: send survey to HIV Syndicate and widely though other channels |  | NASTAD planning meeting |  |  |  |  | NASTAD planning meeting |  |  |  |  | NASTAD planning meeting |  |  |  |  | NASTAD planning meeting
| Community Survey | [5 empty] | MARCH 14: Survey approved; MARCH 28: Syndicate meeting |  | Survey went out to HIV Syndicate |  |  | Survey extended for an additional 2 weeks |  |  | Survey Closed | Analyzed by Heather Posner and Lisa Starr
CDR Recurring Meetings (Internal\External)
internal | Bi weekly HIV CD&R meetings (CO Only) |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  | FEBRUARY 8: C\O Cluster Workgroup; FEBRUARY 22: C\O Cluster Workgroup; MARCH 14: C\O Cluster Workgroup; MARCH 28: C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup |  |  | C\O Cluster Workgroup |  | C\O Cluster Workgroup
internall | Monthly HIV CD&R meetings (CO and HDs) | Statewide CDR Call |  |  |  |  | FEBRUARY 1: Statewide CDR Call; MARCH 7: Statewide CDR Call |  | Statewide CDR Call |  |  |  |  | Statewide CDR Call |  |  |  |  | Statewide CDR Call |  |  |  |  | Statewide CDR Call
| Houston\DSHS Cluster Coordination Call |  | Monthly Coordination Call |  |  |  | FEBRUARY 8: Monthly Coordination Call; MARCH 14: Monthly Coordination Call |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call |  |  |  |  | Monthly Coordination Call
| EHE Pillar 4 Respond Call | [32 empty] | C\O and EHE programs call | [5 empty] | C\O and EHE programs call |  |  |  |  | C\O and EHE programs call |  |  |  |  | C\O and EHE programs call |  |  |  | C\O and EHE programs call |  |  |  |  | C\O and EHE programs call
Trainings/Community Engagement
| NASTAD CD&R community input meetings | [41 empty] | Week 1 Session: HIV Surveillance | Week 2 Session: CDR | Week 3 Session: HIV Criminalization and Stigma
DSHS | Data Security and confidentiality (e-course, ongoing)
req/cardera | HIV Navigation in Texas (HNT) |  |  |  | 2021-01-21 |  | FEBRUARY 15: 2021-02-18; MARCH 14: 2021-03-18 |  |  | 2021-04-15 | [9 empty] | 2021-06-17 | [10 empty] | 2021-08-19 | [7 empty] | 2021-10-03 | [10 empty] | 2021-12-16
| Gender and Sexual Diversity Training (live/virtual) |  |  |  | 2021-01-28 |  | MARCH 21: 2021-03-25 |  |  |  |  | 2021-04-29 | [6 empty] | 2021-06-03 | [10 empty] | 2021-08-12 |  |  |  |  | 2021-09-16 |  |  |  | 2021-10-07 | [7 empty] | 2021-11-30
req/cardera | Gender and Sexual Diversity Training (e-course, ongoing)
Trauma Informed Care (e-course, ongoing)
req/cardera | Trauma Informed Care (live/virtual) | [5 empty] | FEBRUARY 8: 2021-02-11 |  | 2021-04-08 | [6 empty] | 2021-05-18 | [7 empty] | 2021-07-01 | [9 empty] | 2021-09-09 | [9 empty] | 2021-11-04
req/cardera | Health Equity Training
req/TRAIN | HIV Surveillance (6) modules, online
DSHS | DSHS HIPAA and State Privacy
req/cardera | Foundations of Testing and Navigation (FTN) |  | Jan 11-20 |  |  |  | FEBRUARY 22: Feb 22 - 3/3 | [6 empty] | May 10-18 |  |  |  |  | June 14-22 | [15 empty] | Sept 13-21 | [8 empty] | Nov 8-16
| FTN Booster Course | [17 empty] | 2021-04-20 | [10 empty] | 2021-06-29 |  |  |  | 2021-07-20 | [14 empty] | 2021-10-19 | [8 empty] | 2021-12-14
req/TRAIN | STD What you Need to Know
req/TRAIN | Passport to Partner Services
req | Fundamentals of STD Intervention
req/DSHS | Integrated TB/HIV/STD database (THISIS) Training
req/various | Motivational Interviewing | [5 empty] | MARCH 28: 2021-03-31 | [6 empty] | 2021-05-05 | [14 empty] | 2021-08-04 |  |  |  |  | 2021-09-01 |  |  |  |  | 2021-10-06 |  |  |  |  | 2021-11-03 |  |  |  |  | 2021-12-01
CDC/CAI | Social Network Strategy (SNS) | [5 empty] | MARCH 28: 2021-03-26 | [6 empty] | 2021-05-03
Introduction to HIV evolution for HIV-TRACE
Operating Secure HIV-TRACE (CDC has user guides)
Social Media - Facebook, Twitter, YouTube, LinkedIn
| STD Awareness Week | [16 empty] | 2017-04-11
| National Black HIV/AIDS Awareness Day | [5 empty] | FEBRUARY 8: 2021-02-07
World AIDS Day
| National Women and Girls HIV/AIDS Awareness Day | [5 empty] | MARCH 7: 2021-03-05
| National HIV Testing Day | [28 empty] | 2021-06-27
Traditional Media Outreach - All PRN
resource/resp | PSA -audio for web and traditional
resource/resp | PSA - video for web
response | Press Releases - for traditional media and web
Press Release - PWID
Press Release - MSM
Other Online
resource | Website - Resource page for HIV Cluster Detection/Response | [30 empty] | Begin development |  |  |  |  | Draft for manager approval |  |  |  |  | Website goes live
response | Website - health alert - PRN
response | GovDev - health alert - PRN
Other - mailings/handouts
Letter to Providers PRN
MHS English/Spanish handouts
Other Houston handouts we want
Prep handouts
PeP
HIV Testing
IVDU
Condom usage
Safe Sex handout
Fact sheets - syringes
Ongoing meetings/list serv for engagement and response
ad-hoc | Statewide Health Equity Stakeholders
ad-hoc | HIV Workforce Social Media
weekly | HIV Care Services/AA Weekly Email blast
weekly | Achieving Together Newsletter
weekly/ad-hoc | HIV Prevention Contractors
monthly | Eligibility Sub Committee
monthly | Formulary Sub Committee
monthly | PHFU Leadership Call
monthly | San Antonio HIV & Syphilis Testing Task Force
monthly | ESESHA of San Antonio
monthly | Health Improvement Team of Tarrant County
monthly | Ending the Epidemic Coordinators and Planning Groups for Austin, Dallas, San Antonio and Tarrant Counties
monthly | THMP Listservs for Eligibility, Pharmacy, and News
monthly/ad-hoc | FUNdamentals Calls
monthly/annual | HIV Surveillance Sites
monthly/bi-annual | Texas HIV Part A and Part B Planners
quarterly | Medication Advisory Committee
quarterly | First Line Supervisor Group
quarterly | DSHS HIV Care Services Clinical Panel
quarterly | Ryan White SATGA/HSDA CQM Quality Management Committee
quarterly | Dallas External CQM Committee
quarterly | East Texas Coalition
quarterly | South Texas Development Council Administrative Agency Ryan White Part-B Quality Management Advisory Committee Meeting
quarterly | BVCOG Clinical Quality Management Committee
quarterly | Starcare CQM Committee
quarterly | Texas HIV Syndicate Weekly Newsletter
quarterly | Texas Transgender Alliance
ad-hoc | RLHD list, phone calls/emails
Note on A60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Posner,Heather (DSHS) who do we get these handouts from?